## Sheet1
Track | Applications | Assigned Resources | Total # of Test Scenarios | Completed # of Scenarios | Completion % | Blocked Scenarios | Comments
ERP FIN | Bloomberg | Vignesh Pandian | 21 | 4 | 19% | 17 | GET API Call is failing - Invalid IP, IP 98.99.236.29 not allowlisted- unauthorized-client
| Blackline |  | 14 | 14 | 100%
| SAP Ariba |  | 19 | 18 | 95% |  | NiFi processors are up and running. But files are not reaching EBS
| STR | [5 empty] | No Scope defined- QA automation team to update
| Go-Web Form | [5 empty] | Planned after Aug release as per the plan
| High Radius |  | 16 | 12 | 75% | 4 | Invoice not availabe in STR Upgraded server -Working with oracle DBA
FEDS | RMS | Ravi Tutika | 10 | 3 | 30%
| Solstice | Kowsalya | 33 | 15 | 45%
| RAS | Jyotsana Trivedi | 12 | 11 | 92%
| FDP |  | 45 | 5 | 11%
| Treasury |  | 10 | 10 | 0%